## Slide 1: Decommissioning the University of Iowa MC17 Cyclotron
Tom Hansen, CHP, PMP
Ameriphysics, LLC

## Slide 2: Introduction

## Slide 3: Introduction
Scanditronix MC17 particle accelerator
18O(p,n)18F
14N(d,n)15O
14N (p,α)11C
16O(p,α)13N
Operated @ 30 uA, 6 hours/week for last 10 years

## Slide 4: Pre-Characterization

## Slide 5: Characterization

## Slide 6: Characterization
Major Activation Products | Primary Source
Be-7 | target material
Na-22 | aluminum, magnesium
Na-24 | aluminum
Sc-48 | titanium
Cr-51 | target material
Mn-52 | target material
Mn-54 | copper, brass
Co-56 | target material
Mn-56 | copper, brass
Co-57 | target material
Ni-57 | nickel
Co-58 | nickel
Fe-59 | iron
Co-60 | copper, concrete
Zn-65 | copper, brass
Sb-124 | alloys in solder and ball bearings
Total Activity: 137 mCi

## Slide 7: Characterization
Chart: Time (years)
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20

Be-7 | 44.7086 | 0.37695 | 0.0031781 | 2.6795e-05 | 2.2592e-07 | 1.9048e-09 | 1.6059e-11 | 1.354e-13 | 1.1416e-15 | 9.6249e-18 | 8.1149e-20 | 6.8419e-22 | 5.7685e-24 | 4.8636e-26 | 4.1006e-28 | 3.4573e-30 | 2.9149e-32 | 2.4576e-34 | 2.0721e-36 | 1.747e-38 | 1.4729e-40
Na-22 | 0.05362 | 0.041074 | 0.031464 | 0.024102 | 0.018463 | 0.014143 | 0.010834 | 0.0082991 | 0.0063573 | 0.0048699 | 0.0037304 | 0.0028576 | 0.002189 | 0.0016768 | 0.0012845 | 0.00098397 | 0.00075374 | 0.00057739 | 0.00044229 | 0.00033881 | 0.00025954
Na-24 | 0.14408 | 1.8794e-177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sc-48 | 0.078219 | 8.5638e-62 | 9.3759e-122 | 1.0265e-181 | 1.1239e-241 | 1.2304e-301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cr-51 | 6.6899 | 0.00057122 | 4.8774e-08 | 4.1646e-12 | 3.556e-16 | 3.0363e-20 | 2.5926e-24 | 2.2137e-28 | 1.8902e-32 | 1.6139e-36 | 1.3781e-40 | 1.1767e-44 | 1.0047e-48 | 8.5786e-53 | 7.3249e-57 | 6.2544e-61 | 5.3404e-65 | 4.5599e-69 | 3.8935e-73 | 3.3245e-77 | 2.8386e-81
Mn-52 | 2.4559 | 5.7576e-20 | 1.3498e-39 | 3.1644e-59 | 7.4185e-79 | 1.7392e-98 | 4.0772e-118 | 9.5585e-138 | 2.2409e-157 | 5.2534e-177 | 1.2316e-196 | 2.8873e-216 | 6.7689e-236 | 1.5869e-255 | 3.7202e-275 | 8.7215e-295 | 0 | 0 | 0 | 0 | 0
Mn-54 | 4.0575 | 1.8027 | 0.80093 | 0.35585 | 0.1581 | 0.070242 | 0.031208 | 0.013865 | 0.0061603 | 0.0027369 | 0.001216 | 0.00054026 | 0.00024003 | 0.00010664 | 4.7381e-05 | 2.1051e-05 | 9.3527e-06 | 4.1553e-06 | 1.8462e-06 | 8.2023e-07 | 3.6442e-07
Co-56 | 7.3805 | 0.27571 | 0.0103 | 0.00038475 | 1.4373e-05 | 5.3692e-07 | 2.0058e-08 | 7.4928e-10 | 2.799e-11 | 1.0456e-12 | 3.9061e-14 | 1.4592e-15 | 5.4509e-17 | 2.0363e-18 | 7.6068e-20 | 2.8416e-21 | 1.0615e-22 | 3.9655e-24 | 1.4814e-25 | 5.5339e-27 | 2.0673e-28
Mn-56 | 0
Co-57 | 3.2576 | 1.2846 | 0.50654 | 0.19974 | 0.078762 | 0.031058 | 0.012247 | 0.0048292 | 0.0019043 | 0.0007509 | 0.0002961 | 0.00011676 | 4.6041e-05 | 1.8155e-05 | 7.159e-06 | 2.823e-06 | 1.1132e-06 | 4.3895e-07 | 1.7309e-07 | 6.8252e-08 | 2.6914e-08
Ni-57 | 0.20624 | 1.0694e-74 | 5.545e-148 | 2.8751e-221 | 1.4908e-294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 8: Establish Removal Path

## Slide 9: Establish Removal Path

## Slide 10: Establish Removal Path

## Slide 11: Package Ancillaries

## Slide 12: Package Ancillaries

## Slide 13: Remove RF Shield

## Slide 14: Material Handling

## Slide 15: Material Handling

## Slide 16: Material Handling

## Slide 17: Material Handling

## Slide 18: Material Handling

## Slide 19: Material Handling

## Slide 20: Material Handling

## Slide 21: Material Handling

## Slide 22: Material Handling

## Slide 23: Loading and Shipping

## Slide 24: Loading and Shipping

## Slide 25: Loading and Shipping

## Slide 26: Loading and Shipping

## Slide 27: Project Metrics
LLRW shipped for disposal: 48,000 lbs.
Time: 324 person-hours over 3 day period
Cost: ~$200,000
Dose: 53 person-mrem (16 mrem max exposed individual)